2006-2007 MAINTENANCE PROJECTS

	PROJECTS
	START DATE
	END DATE

	Equipment move Tool & Die Lab
	05/01/06
	06/08/07

	Equipment move Auto Tech upper lab
	05/28/07
	06/05/07

	Paint walls Tool & Die Lab
	06/06/07
	06/08/07

	Painting of floor Tool & Die Lab
	06/11/07
	06/15/07

	Paint Drafting & Design and Art class rooms
	06/11/07
	06/29/07

	Rewire lights in Drafting & Design
	06/11/07
	06/29/07

	Install new electrical service in Elect Engineering
	6/11/07
	6/29/07

	Pluming rework in Cosmo Lab
	06/11/07
	8/17/07

	Re install Equipment in Tool & Die lab
	06/25/07
	07/27/07

	Remove furniture in Student Services, room 35 and 36
	07/02/07
	07/03/07

	Painting of floor upper Auto Tech Lab
	07/02/07
	07/13/07

	Install new electrical service in server room
	07/02/07
	07/13/07

	Remove under ground fuel tank at Skill Center
	07/02/07
	8/17/07

	Install Johnson Control update to Metasys HVAC system
	07/02/07
	8/17/07

	Recoat and repair parking lots
	07/02/07
	8/17/07

	HVAC unit install Student Services and Auto Tech lower Theory
	07/02/07
	08/17/07

	Carpet install in Student Services, room 35 and 36 
	07/02/07
	08/17/07

	Install new duct work in Admin Office
	07/02/07
	08/17/07

	Install Simplex update to fire Alarm System at HS
	07/02/07
	08/17/07

	Reinstall Equipment in Auto Tech Lab
	8/6/07
	8/17/07

	Reinstall furniture in Student Services, room 35 and 36
	8/6/07
	8/17/07

	
	
	


