SUMMER 2008 MAINTENANCE PROJECTS

	PROJECTS
	START DATE
	END DATE

	Paint Guidance and Admission’s offices
	06/11/08
	06/29/08

	Paint lockers for art
	06/11/08
	06/29/08

	Summer Maintenance of exfans on roofs
	06/09/08
	06/20/08

	Remove furniture from Room 209-210 at the Skill Center and install new furniture
	06/16/08
	06/27/08

	Remove furniture in Early Childhood Ed classroom, Guidance and Admission’s offices
	07/01/08
	07/02/08

	Carpet install in Early Childhood Ed classroom, Guidance and Admission’s offices
	07/01/08
	07/31/08

	Update Camera system for high school
	07/01/08
	8/17/08

	Install Johnson Control update to Metasys HVAC system
	07/01/08
	8/17/08

	Recoat and repair parking lots
	07/01/08
	8/17/08

	Rebuild Heating valve in Construction Trades lab
	07/01/08
	7/03/08

	HVAC exfan install in Grafts and Art room
	07/01/08
	08/17/08

	Rewire lights in Drafting & Design
	07/07/08
	07/11/08

	Rewire Kitchen power drops
	07/14/08
	07/18/08

	Move under light in Eagles nest
	07/21/08
	07/23/08

	Install new power for laminator
	07/24/08
	07/25/08

	Install new service for Electronics office
	07/28/08
	07/30/08

	Reinstall furniture in Early Childhood Ed classroom, Guidance and Admission’s offices
	08/1/08
	08/17/08

	Install projectors in room 35 and Eagles nest
	08/01/08
	08/08/08

	
	
	

	
	
	

	
	
	

	
	
	

	
	
	

	
	
	


