| # Status Report | Overall Status: On Track |
| --- | --- |

May 24, 2014

| ## Status Code Legend |  |
| --- | --- |
| On Track: Project is on schedule | - High Risk: At risk, with a high risk of going off track |
| - At Risk: Milestones missed but opportunity still exists | - Off Track: Opportunity will be missed if action not taken |

| The project is On Track the month of June 2014, due to the following: | Continued networking Continued Marketing Continued support from Core Group MyFanClip Trolley Tour 100 + businesses, nonprofits & schools registers - (partially due to addition of Summer JAM, where Career Street is able to glean business & nonprofit registrant information) |
| --- | --- |
| Issues: | Currently, there are no issues or concerns. In the past the website has been listed here, however we are coming along well with the tweaking |
| Milestones accomplished the timeframe June 2014 | Outreach ongoing Group presentations ongoing Met with Government Officials |
| Milestones planned this timeframe from 100 day plan, but not achieved with variance: | Connected with all Principals Connected with Guidance Counselors - Because school is out… will follow up this fall Created a website tutorial |
| Milestones planned for next month: | Newsletter Continued Outreach Reporting Plan Next 100 Days |
| Areas/questions for discussion: |  |
| Last month’s issues forwarded to this month: | none |

# Contact Information

| Jennifer Nygaard Pontzer 814.464.8614 814.520.8376 JPontzer@CareerStreetErie.Org |  |
| --- | --- |