| # Status Report | Overall Status: On Track |
| --- | --- |

May 24, 2014

| ## Status Code Legend |  |
| --- | --- |
| On Track: Project is on schedule | - High Risk: At risk, with a high risk of going off track |
| - At Risk: Milestones missed but opportunity still exists | - Off Track: Opportunity will be missed if action not taken |

| The project is On Track the month of May 2014, due to the following: | Continued networking Continued Marketing Continued support from Core Group |
| --- | --- |
| Issues: | Website: continuing to fine tune |
| Milestones accomplished the timeframe May 2014 | Outreach ongoing Group presentations ongoing Met with all community Chambers |
| Milestones planned this timeframe from 100 day plan, but not achieved with variance: | Connected with all Principals Connected with Guidance Counselors Created a website tutorial |
| Milestones planned for next month: | Website tweaking & reporting Connecting with Principals and guidance counselors (per 100 day plan) Planning Summer Outreach Trolley Tour Seawolves Event MyFanClip Newsletter |
| Areas/questions for discussion: |  |
| Last month’s issues forwarded to this month: | none |

# Contact Information

| Jennifer Nygaard Pontzer 814.464.8614 814.520.8376 JPontzer@CareerStreetErie.Org |  |
| --- | --- |