## A9R8DF2
Erie County Technical School--Two Phase Project Plan TE# 2015.01 12-Jan-15
| Item | Description | Cost Estimate | ACT 129 Funding (Y / N) | Comments
Phase 1 | 2016-2017 | High School
| 2016-HS1 | Replace Boilers | 298700 | Y | High efficiency pumps & motors, variable speed drives
| 2016-HS2 | Replace Split Chiller | 334750 | Y | Flush & clean existing piping system
| 2016-HS3 | Renovate Existing Toilet Rooms | 350000 | N
| 2016-HS4 | Replace Exposed Plumbing Piping | 221728 | N | Sanitary, hot water, cold water
| 2016-HS5 | Replace Plumbing Fixtures + Partial Flooring | 130864 | N
| 2016-HS6 | Replace Low Voltage Systems | 601150 | N | Fire alarm, clock, intercom, lighting controls
| 2016-HS7 | Replace Power Systems | 1202300 | N | Service, switchgear, branch distribution, switchboards, sub-panels
| 2016-HS8 | Add Wet Sprinklers | 360690 | N
| 2016-HS9 | Replace Ceilings | 750000 | N
| 2016-HS10 | Replace Windows | 600000 | Y
| 2016-HS11 | Replace Roof | 1400000 | Y
| 2016-HS12 | Exterior Door Replacement | 250000 | Y
| 2016-HS13 | Interior Renovations | 1000000 | Y
| 2016-HS14 | Replace HVAC Hydronic Piping | 480920 | N
| 2016-HS15 | Replace Air Handling Units & Unit Ventilators | 1750485 | Y | Clean duct systems where possible. Remove & reinstall ceiling. Roofing.
| 2016-HS16 | Replace Rooftop Units & PTAC's in Business Office | 113300 | Y | Clean duct systems where possible. Remove & reinstall ceiling. Roofing.
|  | 2016 HS Subtotal | 9844887 |  | 1.5 Years for completion
| 2016-2017 | Skill Center
| 2016-SC1 | Renovate Existing Toilet Rooms | 150000 | N
| 2016-SC2 | Replace Exposed Plumbing Piping | 91237 | N | Sanitary, hot water, cold water
| 2016-SC3 | Replace Low Voltage Systems | 281994 | N | Fire alarm, clock, intercom, lighting controls
| 2016-SC4 | Replace Power Systems | 516989 | N | Service, switchgear, branch distribution, switchboards, sub-panels
| 2016-SC5 | Add Wet Sprinklers | 140997 | N
| 2016-SC6 | Replace Ceilings | 250000 | N
| 2016-SC7 | Replace Windows | 125000 | Y
| 2016-SC8 | Replace Roof | 600000 | Y
| 2016-SC9 | Exterior Door Replacement | 65000 | Y
| 2016-SC10 | Interior Renovations | 500000 | Y
| 2016-SC11 | Replace Plumbing Fixtures + Partial Flooring | 59681 | N
| 2016-SC12 | Replace Makeup Air Units & Multizone Units, DDC Controls | 708640 | Y | Clean duct systems where possible. Remove & reinstall ceiling. Roofing.
|  | 2016 SC Subtotal | 3489538 |  | 1.5 Years for completion
| 2016--Both | Contingency (10%) | 1333442.5
| 2016--Both | Architect & Engineering Fees (6%) | 800065.5
|  | 2016 Grand Total (HS + SC) | 15467933 |  |  | 13334425
Phase 2 | 2019-2020 | High School
| 2019-HS1 | New Addition | 5000000 | Y
| 2019-HS2 | Interior Renovations | 3525000 | Y
|  | 2019 HS Subtotal | 8525000 |  | A 6 to 8 month completion time
| 2019-2020 | Skill Center
| 2019-SC1 | Interior Renovations | 1500000 | Y
|  | 2019 SC Subtotal | 1500000 |  | A 6 to 8 month completion time
| 2019--Both | Contingency (10%) | 1002500
| 2019--Both | Architect & Engineering Fees (6%) | 601500
|  | 2019 Grand Total (HS + SC) | 11629000 |  |  | 10025000
|  | High School Grand Total | 18369887
|  | Skill Center Grant Total | 4989538
|  | Contingency + A & E Fees | 3737508
|  | Project Grand Total | 27096933 |  |  | 23359425
Notes: 1. All cost values were escalated for the year projected to occur in.