| # Status Report | Overall Status: On Track |
| --- | --- |

# September 25, 2014

| ## Status Code Legend |  |
| --- | --- |
| On Track: Project is on schedule | - High Risk: At risk, with a high risk of going off track |
| - At Risk: Milestones missed but opportunity still exists | - Off Track: Opportunity will be missed if action not taken |

| The project is On Track the month of September 2014, due to the following: | Continued networking Continued Marketing Continued support from Core Group 130 + businesses, nonprofits & schools registers |
| --- | --- |
| Issues: | Currently, there are no issues or concerns. In the past the website has been listed here, however we are coming along well with the tweaking |
| Milestones accomplished the timeframe September 2014 | Outreach ongoing Group presentations ongoing Career Street presentations to School District of Erie County Water bottles, MyFanClips presented to all Middle School Teachers (ongoing) Twitter Account |
| Milestones planned this timeframe from 90 day plan, but not achieved with variance: | Website tutorial Survey results distributed At Link Newsletter to website attach documents and photos to website |
| Milestones planned for next month: | Continued Outreach Created a website tutorial |
| Long Term Project Announcements: | Career Fair. This is envisioned as a school day (field trip)Career Fair marketed to 8th grade students throughout Erie County Business After Hours, hosted at ECVTS |
| Last month’s issues forwarded to this month: | None |