Chronology of the ECTS Renovation

RC = Renovation Committee

JOC – Joint Operating Committee

PAC = Superintendents

|  | Event or Action | Notes |
| --- | --- | --- |
| June 2019 | RC requests a meeting with Architect Chris Coughlin to provide his prioritization of projects |  |
| April -- June 2019 | RC meets and continues conversations of prioritizing renovation/replacement need in the ECTS |  |
| May 2019 | Meeting with Legislators at the ECTS | Supportive but did not commit resources |
| April 2019 | RC consensus on approaching Legislators with a request for help/support | It was requested by the RC that ECTS Director Walker prepare a presentation, vetted through the RC, and lead the meeting with Legislators |
| April 2019 | PDE visits the ECTS, tours the facility, and requests financial documents for three years | PDE Representatives: Dr. Lee Burket and Clyde Hornburger |
| April 2019 | PDE interviews/talks with stakeholders | PDE indicates the Governor (Wolf) and Secretary of Education (Rivera) are well informed of the renovation status |
| April 2019 | Legislators contact PDE with request for support in completing the renovation | Deputy Secretary of Education (Mr. Matt Stem) contacts ECTS Director (Dr. Walker) |
| March 2019 | RC began considering a strategy of splitting a renovation into smaller work packages spread out over time |  |
| March-April 2019 | RC formed of selected JOC, PAC members, ECTS Facilities Manager, and ECTS Director |  |
| March-April 2019 | Media coverage of renovation delays |  |
| January – February 2019 | Millcreek publically announces budget deficit and non-participation in ECTS renovation |  |
| AY 2018/2019 | Positive momentum/optimism for renovation |  |
| AY 2018/2019 | Multiple meetings related to renovation design and initial planning |  |
| Fall 2018 | Design work stopped before starting based on JOC concerns about SD approval processes and costs |  |
| Fall 2018 | Initial contract signed for Renovation approved/signed by JOC |  |
| Fall 2018 | Director makes a motion to JOC to select an architect and a design cost not to exceed $32.5M – Motion passes |  |
| Fall 2018 | JOC consideration of seven (7) concept designs |  |
| Fall 2018 | One design concept developed by ECTS Director and Principal | The Director at this time is Dr. Walker and Principal is Mr. Joe Tarasovitch |
| Fall 2018 | Review of renovation concept drawings from 2 architects – HHSDR and HRLC |  |
| August 2018 | New Director Hired at ECTS |  |
| ~Fall 2017/Winter 2018 | JOC hires HHSDR to evaluate HRLC concept drawings and initial cost estimates as a second opinion. HHSDR prepares three design/cost options for JOC |  |
| 2010 – 2017/2018 | Discussion/planning for a renovation is tabled due to financial difficulties for Millcreek SD and completion of the minor renovation |  |
| 2014 | PLANCON is discontinued | PLANCON has been re-offered/discontinued multiple times over the years 2014 -- 2019 |
| 2010 | Minor “renovations” in ECTS – Light fixtures for energy savings | Government emphasis and support for energy savings projects |
| 2009 -- 2910 | ECTS Director visits sending district school board meetings with array of deteriorated pipes and renewed request for a renovation | The Director at this time was Dr. Jackson |
| 2009 | Plumbing repairs reveal multiple pipes leaking water and sewer gas into various spaces with the ECTS | Determined that pipes are buried in concrete floors or masonry walls |
| 1996 - 2019 | Strategy adopted to defer replacement or repair of building systems pending a renovation | Essential system repairs only, multiple non-essential systems go off-line |
| 1996 | Discussion/planning for a renovation is tabled due to financial difficulties for Millcreek SD |  |
| ~1996 | The need for a renovation at ECTS rises in the JOC/PAC |  |

RC = Renovation Committee