## A9R8DF2
Erie County Technical School--Four Year Project Plan TE# 2014.017 22-Jun-14
| Work Item | Description | Construction Cost Estimate | ACT 129 Funding (Y / N) | Comments
Year 1 | 2015-2016 | High School
| 2016-HS1 | Replace Boilers | 298700 | Y | High efficiency pumps & motors, variable speed drives
| 2016-HS2 | Replace Split Chiller | 334750 | Y | Flush & clean existing piping system
| 2016-HS3 | Replace Rooftop Units & PTAC's in Business Office | 113300 | Y | Clean & reuse duct systems where practical. Remove & reinstall ceiling sections as required. TAB work. Roofing
|  | 2016 HS Subtotal | 746750 |  | Could be completed during the summer
| 2015-2016 | Skill Center
| 2016-SC1 | Replace Makeup Air Units & Multizone Units, DDC Controls | 708640 | Y | Clean & reuse duct systems where practical. Remove & reinstall ceiling sections as required. TAB work. Roofing.
|  | 2016 SC Subtotal | 708640 |  | Could be completed during the summer
| 2016--Both | Contingency (10%) | 145539
| 2016--Both | Architect & Engineering Fees (6%) | 87323.4
|  | 2016 Grand Total (HS + SC) | 1688252.4 |  |  | 1455390
Year 2 | 2016-2017 | High School
| 2017-HS1 | Replace Air Handling Units & Unit Ventilators | 1750485 | Y | Clean & reuse duct systems where possible. Remove & reinstall ceiling sections as required. TAB work. Roofing.
| 2017-HS2 | Replace Plumbing Fixtures + Partial Flooring | 130864 | N
| 2017-HS3 | Replace Exposed Plumbing Piping | 221728 | N | Sanitary, hot water, cold water
| 2017-HS4 | Renovate Existing Toilet Rooms | 350000 | N
|  | 2017 HS Subtotal | 2453077 |  | Could be completed during the summer
| 2016-2017 | Skill Center
| 2017-SC1 | Replace Plumbing Fixtures + Partial Flooring | 59681 | N
| 2017-SC2 | Replace Exposed Plumbing Piping | 91237 | N | Sanitary, hot water, cold water
| 2017-SC3 | Renovate Existing Toilet Rooms | 150000 | N
|  | 2017 SC Subtotal | 300918 |  | Could be completed during the summer
| 2017--Both | Contingency (10%) | 275399.5
| 2017--Both | Architect & Engineering Fees (6%) | 165239.7
|  | 2017 Grand Total (HS + SC) | 3194634.2 |  |  | 2753995
Year 3 | 2017-2018 | High School
| 2018-HS1 | Replace Low Voltage Systems | 601150 | N | Fire alarm, clock, intercom, lighting controls
| 2018-HS2 | Replace Power Systems | 1202300 | N | Service, switchgear, branch distribution, switchboards, sub-panels
| 2018-HS3 | Add Wet Sprinklers | 360690 | N
| 2018-HS4 | Replace Ceilings | 750000 | N
| 2018-HS5 | Replace HVAC Hydronic Piping | 480920 | N
|  | 2018 HS Subtotal | 3395060 |  | Would need an April/May start
| 2017-2018 | Skill Center
| 2018-SC1 | Replace Low Voltage Systems | 281994 | N | Fire alarm, clock, intercom, lighting controls
| 2018-SC2 | Replace Power Systems | 516989 | N | Service, switchgear, branch distribution, switchboards, sub-panels
| 2018-SC3 | Add Wet Sprinklers | 140997 | N
| 2018-SC4 | Replace Ceilings | 250000 | N
|  | 2018 SC Subtotal | 1189980 |  | Would need an April/May start
| 2018--Both | Contingency (10%) | 458504
| 2018--Both | Architect & Engineering Fees (6%) | 275102.4
|  | 2018 Grand Total (HS + SC) | 5318646.4 |  |  | 4585040
Year 4 | 2018-2019 | High School
| 2019-HS1 | Replace Windows | 600000 | Y
| 2019-HS2 | Replace Roof | 1400000 | Y
| 2019-HS3 | Exterior Door Replacement | 250000 | Y
| 2019-HS4 | New Addition | 5000000 | Y
| 2019-HS5 | Interior Renovations | 4525000 | Y
|  | 2019 HS Subtotal | 11775000 |  | A 6 to 8 month completion time
| 2018-2019 | Skill Center
| 2019-SC1 | Replace Windows | 125000 | Y
| 2019-SC2 | Replace Roof | 600000 | Y
| 2019-SC3 | Exterior Door Replacement | 65000 | Y
| 2019-SC4 | Interior Renovations | 2000000 | Y
|  | 2019 SC Subtotal | 2790000 |  | A 6 to 8 month completion time
| 2019--Both | Contingency (10%) | 1456500
| 2019--Both | Architect & Engineering Fees (6%) | 873900
|  | 2019 Grand Total (HS + SC) | 16895400 |  |  | 14565000
|  | High School Grand Total | 18369887
|  | Skill Center Grand Total | 4989538
|  | Contingency + A & E Fees | 3737508
|  | Project Grand Total | 27096933 |  |  | 23359425
Notes: 1. All cost values were escalated for the year projected to occur in.
|  | 2014-2015 | 27096933 | 1.03
|  | 2015-2016 | 27909840.99
|  | 2016-2017 | 28747136.2197
|  | 2017-2018 | 29609550.3063
|  | 2018-2019 | 30497836.8155
|  | 2019-2020 | 31412771.9199

## A9R8DF2 (2)
| Erie County Technical School--Four Year Project Plan TE# 2014.017 22-Jun-14 | [6 empty] | 1.04 | 1.045
| Work Item | Description | Construction Cost Estimate | ACT 129 Funding (Y / N) | Comments
Year 1 | 2015-2016 | High School
| 2016-HS1 | Replace Boilers | 298700 | Y | High efficiency pumps & motors, variable speed drives
| 2016-HS2 | Replace Split Chiller | 334750 | Y | Flush & clean existing piping system
| 2016-HS3 | Replace Rooftop Units & PTAC's in Business Office | 113300 | Y | Clean & reuse duct systems where practical. Remove & reinstall ceiling sections as required. TAB work. Roofing
|  | 2016 HS Subtotal | 746750 |  | Could be completed during the summer
| 2015-2016 | Skill Center
| 2016-SC1 | Replace Makeup Air Units & Multizone Units, DDC Controls | 708640 | Y | Clean & reuse duct systems where practical. Remove & reinstall ceiling sections as required. TAB work. Roofing.
|  | 2016 SC Subtotal | 708640 |  | Could be completed during the summer
| 2016--Both | Contingency (10%) | 145539
| 2016--Both | Architect & Engineering Fees (6%) | 87323.4
|  | 2016 Grand Total (HS + SC) | 1688252.4 |  |  |  | 1455390
Year 2 | 2016-2017 | High School
| 2017-HS1 | Replace Air Handling Units & Unit Ventilators | 1750485 | Y | Clean & reuse duct systems where possible. Remove & reinstall ceiling sections as required. TAB work. Roofing.
| 2017-HS2 | Replace Plumbing Fixtures + Partial Flooring | 130864 | N
| 2017-HS3 | Replace Exposed Plumbing Piping | 221728 | N | Sanitary, hot water, cold water
| 2017-HS4 | Renovate Existing Toilet Rooms | 350000 | N
|  | 2017 HS Subtotal | 2453077 |  | Could be completed during the summer
| 2016-2017 | Skill Center
| 2017-SC1 | Replace Plumbing Fixtures + Partial Flooring | 59681 | N
| 2017-SC2 | Replace Exposed Plumbing Piping | 91237 | N | Sanitary, hot water, cold water
| 2017-SC3 | Renovate Existing Toilet Rooms | 150000 | N
|  | 2017 SC Subtotal | 300918 |  | Could be completed during the summer
| 2017--Both | Contingency (10%) | 275399.5
| 2017--Both | Architect & Engineering Fees (6%) | 165239.7
|  | 2017 Grand Total (HS + SC) | 3194634.2 |  |  |  | 2753995
Year 3 | 2017-2018 | High School
| 2018-HS1 | Replace Low Voltage Systems | 601150 | N | Fire alarm, clock, intercom, lighting controls
| 2018-HS2 | Replace Power Systems | 1202300 | N | Service, switchgear, branch distribution, switchboards, sub-panels
| 2018-HS3 | Add Wet Sprinklers | 360690 | N
| 2018-HS4 | Replace Ceilings | 750000 | N
| 2018-HS5 | Replace HVAC Hydronic Piping | 480920 | N
|  | 2018 HS Subtotal | 3395060 |  | Would need an April/May start
| 2017-2018 | Skill Center
| 2018-SC1 | Replace Low Voltage Systems | 281994 | N | Fire alarm, clock, intercom, lighting controls
| 2018-SC2 | Replace Power Systems | 516989 | N | Service, switchgear, branch distribution, switchboards, sub-panels
| 2018-SC3 | Add Wet Sprinklers | 140997 | N
| 2018-SC4 | Replace Ceilings | 250000 | N
|  | 2018 SC Subtotal | 1189980 |  | Would need an April/May start
| 2018--Both | Contingency (10%) | 458504
| 2018--Both | Architect & Engineering Fees (6%) | 275102.4
|  | 2018 Grand Total (HS + SC) | 5318646.4 |  |  |  | 4585040
Year 4 | 2018-2019 | High School
| 2019-HS1 | Replace Windows | 600000 | Y
| 2019-HS2 | Replace Roof | 1400000 | Y
| 2019-HS3 | Exterior Door Replacement | 250000 | Y
| 2019-HS4 | New Addition | 5000000 | Y
| 2019-HS5 | Interior Renovations | 4525000 | Y
|  | 2019 HS Subtotal | 11775000 |  | A 6 to 8 month completion time
| 2018-2019 | Skill Center
| 2019-SC1 | Replace Windows | 125000 | Y
| 2019-SC2 | Replace Roof | 600000 | Y
| 2019-SC3 | Exterior Door Replacement | 65000 | Y
| 2019-SC4 | Interior Renovations | 2000000 | Y
|  | 2019 SC Subtotal | 2790000 |  | A 6 to 8 month completion time
| 2019--Both | Contingency (10%) | 1456500
| 2019--Both | Architect & Engineering Fees (6%) | 873900
|  | 2019 Grand Total (HS + SC) | 16895400 |  |  |  | 14565000
|  | High School Grand Total | 18369887
|  | Skill Center Grand Total | 4989538
|  | Contingency + A & E Fees | 3737508 | [5 empty] | Act 129 Items - HS Only
|  | Project Grand Total | 27096933 |  |  |  | 23359425 |  | 14272235
Notes: 1. All cost values were escalated for the year projected to occur in.
|  | COST OF HIGH SCHOOL PROJECT | 4% Increase | $$ Amount of Change | 4.5% Increase | $$ Amount of Change
|  | 2014-2015 | 21359893.4 |  | 21359893.4
|  | 2015-2016 | 22214289.136 | 854395.736 | 22321088.603
|  | 2016-2017 | 23102860.7014 | 888571.5654 | 23325537.5901 | 1004448.9871
|  | 2017-2018 | 24026975.1295 | 924114.4281 | 24375186.7817 | 1049649.1916
|  | 2018-2019 | 24988054.1347 | 961079.0052 | 25472070.1869 | 1096883.4052
|  | 2019-2020 | 25987576.3001 | 999522.1654 | 26618313.3453 | 1146243.1584
This table assumes a 4% or 4.5% annual increase and that 80% of the total Contingency + A&E Fees are attributable to High School Project
Did not include Skill Center within the 2014-2015 base cost in the table above
Potential Act 129-Eligible Items (High School Only) in above schedules totaled $14,272,235