## January
Project Status up to January 31st 2022
Prime Contractor | Total Contract | Retainage | Bond/Mobilization/Salaries | Percentage BMS | Completed Work | Percentage CW | Stored Material | percentage SM | Completed Plus Storage | Total Paid to date | Total Percentage
Perry Construction Group | 15749000 | 71549 | 191633 | 1.217% | 414153 | 2.63% | 109706 | 0.6966% | 523859 | 715492 | 4.543%
Church and Murdock | 4850000 | 46096.83 | 300578.75 | 6.197% | 160389.5 | 3.307% | 0 | 0% | 160389.5 | 460968.25 | 9.505%
D&G Mechanical | 6281000 | 11900 | 72900 | 1.161% | 34200 | 0.5445% | 0 | 0% | 34200 | 107100 | 1.705%
Scobell Plumbing | 2719000 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0%
Totals | 29599000 | 129545.83 | 565111.75 | 1.909% | 608742.5 | 2.057% | 109706 | 0.3706% | 718448.5 | 1283560.25 | 4.336%

## February
Project Status up to February 28th 2022
Prime Contractor | Total Contract | Retainage | Bond/Mobilization/Salaries | Percentage BMS | Completed Work | Percentage CW | Stored Material | percentage SM | Completed Plus Storage | Total Paid to date | Total Percentage
Perry Construction Group | 15749000 | 71549 | 191633 | 1.217% | 414153 | 2.63% | 109706 | 0.6966% | 523859 | 715492 | 4.543%
Church and Murdock | 4850000 | 103191.34 | 300578.75 | 6.197% | 450339.16 | 9.285% | 177804.05 | 3.666% | 628143.21 | 928721.96 | 19.15%
D&G Mechanical | 6281000 | 28546 | 81000 | 1.29% | 175914 | 2.801% | 0 | 0% | 175914 | 256914 | 4.09%
Scobell Plumbing | 2719000 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0%
Totals | 29599000 | 203286.34 | 573211.75 | 1.937% | 1040406.16 | 3.515% | 287510.05 | 0.9714% | 1327916.21 | 1901127.96 | 6.423%

## March
Project Status up to February 28th 2022
Prime Contractor | Total Contract | Retainage | Bond/Mobilization/Salaries | Percentage BMS | Completed Work | Percentage CW | Stored Material | percentage SM | Completed Plus Storage | Total Paid to date | Total Percentage
Perry Construction Group | 15749000 | 71549 | 191633 | 1.217% | 414153 | 2.63% | 109706 | 0.6966% | 523859 | 715492 | 4.543%
Church and Murdock | 4850000 | 103191.34 | 300578.75 | 6.197% | 450339.16 | 9.285% | 177804.05 | 3.666% | 628143.21 | 928721.96 | 19.15%
D&G Mechanical | 6281000 | 28546 | 81000 | 1.29% | 175914 | 2.801% | 0 | 0% | 175914 | 256914 | 4.09%
Scobell Plumbing | 2719000 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 0%
Totals | 29599000 | 203286.34 | 573211.75 | 1.937% | 1040406.16 | 3.515% | 287510.05 | 0.9714% | 1327916.21 | 1901127.96 | 6.423%

## Contingency - Other
Contingency
Prime Contractor | Original Contract | New Contract | Other Costs | Change
Perry Construction Group | 15749000 | 15815406 |  | 66406
Church and Murdock | 4850000 | 4872186.5 |  | 22186.5
D&G Mechanical | 6281000 | 6281000 |  | 0
Scobell Plumbing | 2719000 | 2719000 |  | 0
Total Prime Change Orders |  |  |  | 88592.5
Building permit |  |  | 147829.89 | 147829.89
Storm water Permit |  |  | 1510 | 1510
Builders Risk |  |  | 44160 | 44160
Copy King |  |  | 2140.71 | 2140.71
Salary Clerk of the Works |  |  | 17108 | 17108
Meuller locksmith |  |  | 155 | 155
Wilkins Co |  |  | 1195 | 1195
Cernica Engineering Co |  |  | 1764 | 1764
Totals | 29599000 | 29687592.5 | 195640.6 | 284233.1

## Change Order Perry
Change Order Summary Perry
CO # | Date | Pay App | Additions | Cost | Deductions | Cost | Difference
0
# 1 | 2022-02-28 | # 5 | Temp Moves /Materials | 38756
# 1 | 2022-02-28 | # 5 | Temp Moves /Materials | 15224 |  | 0
# 1 | 2022-02-28 | # 5 | Extend existing Foundation | 11124 |  | 0
# 1 | 2022-02-28 | # 5 | Pier Modification/Fiber Optic | 1302 |  | 0
|  |  |  | 0 |  | 0
|  |  | Total | 66406 |  | 0
|  |  | Original Contract | 15749000 | Original Contract | 15749000
|  |  | Add Total | 66406 | Deduct Total | 0
|  |  | Sub Total | 15815406 | Sub Total | 15749000 | 66406
[6 empty] | Original Contract | 15749000
[6 empty] | Difference | 66406
[6 empty] | New Contract | 15815406

## Change Orders Church & Murdock
Change Order Summary Church and Murdock
CO # | Date | Pay App | Additions | Cost | Deductins | Cost | Difference
# 1 | 2022-01-04 |  | Power study panel upgrade | 5090 |  | 0
# 2 | 2022-01-22 | # 4 | Temp Nurse Station | 2678.5 |  | 0
# 3 | 2022-02-22 | # 4 | Move PA line to temp HS Office | 1113
# 4 | 2022-02-22 | # 4 | Relocate Early Childood class | 2309
# 5 | 2/82022 |  | Card Readers | 3572
# 6 | 2022-02-08 |  | Temporary classrooms | 7079 |  | 0
# 7 | 2022-02-08 |  | Temp office receptacle | 345 |  | 0
|  |  | #VALUE! | 22186.5 |  | 0
xxxxv b
|  |  | Original Contract | 4850000 | Original Contract | 4850000
|  |  | Add Total | 22186.5 | Deduct Total | 0
|  |  | Sub Total | 4872186.5 | Sub Total | 4850000 | 22186.5
[6 empty] | Original Contract | 4850000
[6 empty] | Difference | 22186.5
[6 empty] | New Contract | 4872186.5

## Change Orders D&G
Change Order Summary D&G
Additions | Cost | Deductins | Cost | Difference
Card Readers | 0
Temporary classrooms | 0 |  | 0
Temp office receptacle | 0 |  | 0
| 0 |  | 0
| 0 |  | 0
Total | 0 |  | 0
Original Contract | 6281000 | Original Contract | 6281000
Add Total | 0 | Deduct Total | 0
Sub Total | 6281000 | Sub Total | 6281000 | 0
|  |  | Original Contract | 6281000
|  |  | Difference | 0
|  |  | New Contract | 6281000

## Cange Orders Scobell
Change Order Summary Scobell
Additions | Cost | Deductins | Cost | Difference
Card Readers | 0
Temporary classrooms | 0 |  | 0
Temp office receptacle | 0 |  | 0
| 0 |  | 0
| 0 |  | 0
Total | 0 |  | 0
Original Contract | 2719000 | Original Contract | 2719000
Add Total | 0 | Deduct Total | 0
Sub Total | 2719000 | Sub Total | 2719000 | 0
|  |  | Original Contract | 2719000
|  |  | Difference | 0
|  |  | New Contract | 2719000